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BRANTLEY COUNTY HAZARD MITIGATION PLAN UPDATE

REQUEST FOR PROPOSAL #P
PROPOSAL DUE: 

20

REQUEST FOR PROPOSALS
BRANTLEY COUNTY HAZARD MITIGATION PLAN
Proposal Number: P

The Brantley County Board of Commissioners is seeking proposals from qualified firms to update the County’s Hazard Mitigation Plan. Proposals will be received in the office of the County Clerk, 33 Allen Rd, Nahunta, Georgia 31553, until August 14, 2026. All proposals must be picked up no later than 2 pm. You will also have access to download the proposal from the Brantley County Government site until this time. No proposals may be withdrawn after the closing time for the receipt of proposals for a period of ninety (90) days. 

SOLICITATION SCHEDULE:
	Request for Proposal				July 8, 2026
Deadline for questions		            July 31, 2026
Answers to questions				August 7, 2026
Proposal Due Date				August 14, 2026
Public Proposal Opening			August 25, 2026
Board of Commissioners Approval		September 8, 2026
Letter of Intent to Award                    	September 11, 2026
Draft of Hazard Mitigation			December 4, 2026
Grant Close Out				December 18, 2026
Plan Approved By				January 12, 2027

SUBMISSION: One (1) original and three (3) copies of the required proposal documents must be submitted in a sealed envelope marked “BRANTLEY COUNTY HAZARD MITIGATION PLAN”- Proposal # ___, mailed or dropped off at the address below.
	U.S. Postal Service/FedEx/UPS:
Brantley County Board of Commissioners
Attn: County Clerk
33 Allen Rd
Nahunta Ga 31553
	


The proposal opening will be held in person on August 25, 2026, at 2 pm at the Board of Commissioners’ Office, located at 33 Allen Rd, Nahunta, GA 31553.  Proposals received after the required time or in any location other than the County Clerk’s office will not be accepted. Brantley County will not be held liable for misdirected deliveries or deliveries that are late due to the shipping carrier. Faxed or emailed submissions will not be accepted.

All proposals submitted in response to this request shall become the property of Brantley County and will be public records available for review after award. Please note that failure to meet any of the requirements stipulated within this RFP will result in the disqualification of the Contractor. It is incumbent upon each Contractor to thoroughly review the RFP and ensure their proposal fully meets all specified requirements.

Proposals may be withdrawn by written request only if the request is received prior to the time and date set for the opening of proposals. Negligence by the proposer in preparing his proposal confers no right of withdrawal or modification of the proposal after it has been opened. No proposal may be withdrawn for a period of ninety (90) days after the time and date of opening of proposals.
Brantley County reserves the exclusive right to determine which Proposer should be awarded the Contract. Brantley County also reserves the right to waive any irregularity or informality in a proposal and to accept or reject any item or combination of items when doing so would benefit Brantley County. Also, Brantley County may reject proposals that do not include all requested elements and information. Brantley County will not be liable for any costs or losses incurred by proposers throughout this process. Brantley County does not discriminate on the basis of race, religion, color, sex, national origin, age, or disability.

The Proposer will indemnify, defend, and hold harmless Brantley County from and against any and all claims, damages, losses, and expenses including, but not limited to, fees and charges of attorneys and court and arbitration costs, arising out of or resulting from the negligent acts, negligent omissions, willful misconduct, or reckless misconduct of the Proposer or anyone for whom the Proposer is responsible.

Questions regarding this project may be directed in writing to the County Clerk, Taylor Sheppard, at bclerk@brantleycountyga.gov. All questions shall be received by ____ and answered by ____.

BACKGROUND:

The contractor will update the existing Brantley County, Georgia, Multi-Jurisdictional Mitigation Plan in accordance with the requirements of the Disaster Mitigation Act of 2000. This scope of work was designed in conformance with FEMA Plan Guidance requirements. If you would like a copy of the current plan, you can email the Emergency Manager Director at ema@brantleycounty-ga.gov to request one. 

CONDITIONS:

Brantley County and participating municipalities will update their Multi-Jurisdictional Hazard Mitigation Plan to meet FEMA's Disaster Mitigation Act of 2000 five (5)- year update requirements. The planning process implemented through this grant must comply with the Local Hazard Mitigation Planning requirement contained in 44 CFR 201. A complete draft plan document must be submitted to the State and our office for review and comment at least six (6) months prior to the grant's completion, so that any necessary revisions may be made prior to adoption and during the period of performance. 

The final plan documents must be submitted for review and approval prior to the end of the grant's period of performance, and FEMA approval must be obtained prior to grant closeout. The contractor will adhere to all sections of the scope of work and the milestones listed in the associated grant application. The contractor will include all HAZUS Level II analyses provided by GEMA/HS in the risk assessment and utilize the information to update their goals, objectives, and action steps. 

The selected contractor will be responsible for developing a comprehensive FEMA-compliant Hazard Mitigation Plan (HMP) with minimal reliance on local staff. The scope of work includes conducting a thorough risk assessment, identifying and analyzing potential hazards, developing mitigation strategies, and facilitating public and stakeholder engagement throughout the planning process. The contractor must ensure that the plan meets all FEMA requirements for approval, including compliance with the latest FEMA guidance, standards, and regulations. This includes preparing all necessary documentation, coordinating with relevant agencies, and addressing any feedback from FEMA in order to secure plan approval. The contractor must demonstrate expertise in hazard mitigation planning and have the necessary resources and experience to complete the project independently, while keeping local involvement to a minimum.

SCOPE:

The contractor will host planning meetings, as necessary, and a minimum of three (3) public workshops. The contractor will, as needed, coordinate with the GEMA/HS representative to use the necessary tools and ensure the plan complies with the most current Federal regulations. The contractor will be required to complete the following: Critical Facility Inventory and basic mapping will be established in the Georgia Mitigation Information System, including running reports by jurisdiction for each identified hazard; GEMA/HS Worksheets 3A for each participating jurisdiction for each identified hazard; high level detail for all mitigation action steps as required by FEMA and GEMA/HS; ensure all ‘recommended revisions” from their previous FEMA Plan review are addressed in the plan update. 

Additionally, the contractor will ensure the plan update is consistent with the most current requirements from FEMA, including: 
A. Identify all changes to the plan within each section.
B. Update the Planning Process:
1. List jurisdictions participating in the plan to seek approval.
2. Describe the process used to review and analyze each section of the plan, as well as the process used to determine if a section warranted an update. 
C. Improve the Risk Assessment:
1. Address any newly identified hazards that pose a more significant threat than was apparent when the previously approved plan was prepared.
2. Discuss new occurrences of hazard events and update the probability of future occurrences.
3. Incorporate new information where data deficiencies were identified in the previous plan, or if the data deficiencies remain unsolved, explain why they remain unresolved and include a schedule to resolve the issue.
4. Include current inventory of existing and proposed buildings, infrastructure, and critical facilities in hazard areas. The community will determine how far into the future they wish to go in considering proposed buildings and critical facilities, based on and timed with the data-gathering phase of their comprehensive plan or land-use plan update. 
5. The loss estimate should be updated to reflect any changes to the hazard profile and/or the inventory of structures. 
6. Any changes to analysis methodologies must be noted. Any previously noted data deficiencies should be updated or explained.
7. Include a general overview of land uses and types of development occurring within the community and highlight any new and/or relevant information.
8. If there are any changes in the risk assessment of the vulnerability of the community to the hazards, the information must be attributed to the appropriate jurisdiction(s) or to the whole planning area, whichever applies. 
9. Continue to use all available tool sets and data as the GMIS is enhanced (for example: repetitive losses).
D. Analyze, Update, and Continue Development of Goals, Objectives, and Action Steps:
1. Use this update as an opportunity for jurisdictions to reconsider the goals and objectives. For any remaining goals and actions, the plan must document that they were re-evaluated and deemed valid and effective.
2. Goals and objectives shall include the community’s strategy for new or continued NFIP participation. Continue to use the “STAPLEE Criteria” (Social, Technical, Administrative, Political, Legal, Economic, and Environmental), or incorporate them if not previously used, to assess the value and develop an understanding of the cost-effectiveness of mitigation action steps. If actions remain unchanged, the updated plan must explain why no changes are necessary.
3. Shall include evaluation and prioritization for any new mitigation action steps.
E. Update the Plan Maintenance and Implementation:
1.	Must include an analysis of whether the previously approved plan’s method and schedule for monitoring, evaluating, and updating the plan worked, and what elements or processes, if any, were changed; and discuss the method and schedule to be used over the next five (5) years.
2.	Describe other planning mechanisms or ordinances that this plan will be incorporated into, such as Comprehensive Plans.
F. Information Dissemination:	
    1. Describe how the community was kept involved during the plan maintenance process over the previous five (5) years, within the planning process section of the plan update.
    2. The plan maintenance section shall describe how the community will involve the public during the plan maintenance process over the next five (5) years.	
         G. Adoption and Review: 
	    1. The plan will be submitted for State review and recommendation prior to adoption.
    2. Upon recommendation from GEMA/HS, the County and participating municipalities will adopt the plan.
    3. The adopted plan will be submitted for FEMA review and approval.
	H. GIS Overview:
1. The selected consultant will be responsible for summarizing the complete Hazard Mitigation Plan (HMP) using Geographic Information Systems (GIS). This summary must include all key elements and findings of the HMP, with a focus on visually representing hazard data, risks, and mitigation strategies through GIS layers. The consultant will ensure that the GIS deliverables meet FEMA's hazard mitigation planning requirements. The selected consultant will use FEMA's “Risk MAP Project Teams” for technical assistance in mitigation planning throughout the Risk MAP project lifecycle, coordinate with Brantley County GIS, and leverage GIS expertise. 

2. GIS Data Integration and Mapping:
a. Collect and integrate all relevant spatial data identified in the HMP, including, but not limited to, hazard zones (e.g., flood zones, wildfire areas, storm surge, riverine flooding, rain inundation areas, etc., with critical infrastructure, population data, and other community assets.
b. Develop GIS layers for each identified hazard, ensuring data accuracy and alignment with FEMA’s standards.
c. Use GIS tools to map the areas of potential risk and visualize how different hazards overlap with critical community assets.
3. Layered GIS Mapping Deliverables:
a. Create and present GIS maps that include the following layers, at a minimum:
i. Hazard-specific layers (e.g., floodplains, earthquake fault lines, wildfire risk zones).
ii. Critical infrastructure locations (e.g., hospitals, schools, emergency services).
iii. Vulnerable populations (e.g., areas with high density of elderly, low-income, or disabled populations).
iv. Existing and proposed mitigation projects and measures.
b. Ensure each map layer is clearly labeled and includes relevant metadata such as data sources, scale, date, and map legend.
4. Data Analysis and Visualization:
a. Analyze spatial relationships between hazards and community assets to identify areas of high risk and prioritize mitigation strategies.
b. Use GIS tools to create visual representations (e.g., heat maps, risk overlays) to highlight key findings.
c. Prepare a summary of the analysis that includes a description of the methodology, data sources, and findings.
5. Summary Report Preparation:
a. Develop a concise report summarizing the GIS findings and how they align with the HMP’s goals and objectives.
b. Include maps and visualizations as part of the report to enhance understanding of risk assessments and mitigation strategies.
c. Ensure the report is in a format suitable for submission to FEMA, adhering to FEMA’s guidelines for hazard mitigation plan summaries.
6. Presentation and Review:
a. Present the summarized GIS findings to relevant stakeholders, including local government officials and community representatives.
b. Be available for a review meeting with the client and stakeholders to address any questions or requests for additional information.
c. Make necessary revisions to the GIS maps or report based on feedback.
7. Final Deliverables:
a. A comprehensive GIS database with all layers used for the HMP summary, delivered in a format compatible with the client’s GIS software.
b. A summary report in PDF format, including GIS maps and analysis.
c. A digital copy of all GIS maps and layers in both PDF and shapefile formats, with proper documentation and metadata.
8. GIS Requirements:
a. The consultant must have demonstrated experience in GIS analysis and hazard mitigation planning.
b. Familiarity with FEMA’s hazard mitigation plan guidelines and the National Flood Insurance Program (NFIP) is required.
c. All work must be completed within the agreed-upon timeline, with progress updates provided bi-weekly.
d. The consultant will ensure that all work is completed in accordance with FEMA’s requirements for hazard mitigation planning and that the final GIS deliverables provide a clear and effective representation of the community’s risks and mitigation strategies.
e. This scope of work ensures that the consultant focuses on both technical GIS tasks and the specific requirements related to FEMA's hazard mitigation planning. It emphasizes transparency, data accuracy, and alignment with stakeholders' needs.


REQUIREMENTS:
A. Detailed experience in producing at least two (2) FEMA-approved Hazard Mitigation Plans for communities of at least a similar size.
B. Define a Professional Planner serving as the lead coordinator for the update and section development of the Brantley County Multi-Jurisdictional Pre-Disaster Mitigation Plan according to the latest FEMA Plan Guidance Requirements.
C. Coordinate, host, and record all local mitigation planning meetings and workshops (a minimum of three (3) public meetings). Workshops exceeding the minimum of three (3) will be billed at the rate proposed in the Cost Proposal Form.
D. Coordinate through identified Public Information Officers to ensure all meetings are announced and advertised properly.
E. Attend and participate in all State-level planning meetings and workshops.
F. Assess and record Brantley County’s significant hazards.
G. Collect, compile, and analyze the County-wide Critical Facility Inventory and ensure data is uploaded to the state GMIS.
H. Coordinate design and publication of maps, charts, graphs, and worksheets:
1. Coordinate jurisdiction reports for each identified hazard.
2. Ensure a high level of detail for all mitigation strategies and action steps as required by    FEMA and GEMA.
3. Ensure all “recommended revisions” from previous FEMA Plan reviews are addressed and incorporated.
4. Identify all changes to the plan within each section, including revisions to the planning process, risk assessment, goals and objectives, plan maintenance process, etc.

DRAFT PLAN SUBMISSION:
	A draft of the Hazard Mitigation Plan shall be submitted by __________.


CONTRACT TERMS AND CONDITIONS
The Contract with the successful proposer will contain the following contract terms and conditions:

1. Procedures
The extent and character of the services to be performed by the Contractor shall be subject to the general control and approval of the County’s authorized representative(s). Any change to the contract must be submitted in writing and approved by the Director of Emergency Management.

2. Schedule
Proposers shall include a proposed project schedule with their proposal. Failure to include the schedule may constitute sufficient cause to reject the proposal as non-responsive. The actual timing for this project shall be coordinated with the Director of Emergency Management.

3. License Requirement
All firms doing business in Brantley County are required to hold a current, valid business license within the municipality where the home office is located.

4. Insurance
The Contractor shall procure, maintain, and provide proof of insurance coverage for injuries to persons and/or property damage as may arise from or in conjunction with the work performed on behalf of the County by the Contractor, his agents, representatives, employees, or subcontractors. Proof of coverage as contained herein shall be submitted prior to the commencement of work, and the Contractor shall maintain such coverage for the duration of the contract period. The Contractor shall not perform any work unless he has obtained and continues to maintain for the duration of such work such workers' compensation coverage as may be required pursuant to the provisions of Title 34, Chapter 9 of the Official Code of Georgia.

A. Liability.
The Contractor shall maintain such insurance as will protect him from claims under workmen's compensation acts and from any other claims for damages to property, and for personal injury, including death, which may arise from operations under this contract, whether such operations be by himself or by any sub-contractor or anyone directly or indirectly employed by either of them. Such certificates shall be in form and substance reasonably acceptable to the Owner, shall indicate that, except in respect to workers' compensation insurance coverage and professional errors and omissions, Owner is an additional insured with respect to such coverage, and shall indicate that such coverage is primary and not contributory with any similar insurance purchased by the Owner. The certificates shall contain a provision that the insurer will endeavor, if allowed by the policy, to provide Owner with thirty (30) calendar days’ notice of nonrenewal, cancellation, or termination of the coverage. If the successful proposer receives a non-renewal. cancellation or termination notice from an insurance carrier providing coverage required herein, the successful proposer agrees to notify Owner by fax within two (2) business days, with a copy of the nonrenewal, cancellation, or termination notice, or written specifications indicating which coverage is no longer in compliance. Failure to comply with any provision relating to insurance coverage herein shall constitute a material breach if not cured. The contractor shall be responsible for providing adequate limits of insurance when working within property owned by railroads, as established by such railroad company.

B. Indemnity.
To the fullest extent permitted by laws, statutes, rules and regulations, the Contractor shall indemnify and hold harmless the County, Engineer, Engineer’s Consultants and the Officers, Directors, Employees, Agents, and other Consultants of each and any of them from and against claims, costs, damages, losses, and expenses, including but not limited to all fees and charges of engineers, architects, attorneys and other professionals and all court costs, arising out of or resulting from performance of the work, but only to the extent caused in whole or in part by negligent, reckless, willful and wanton, or wrongful acts or omissions of the Contractor, its Officers, Directors, Employees, Agents, and anyone directly, or indirectly employed by them or anyone for whose acts they may be liable, regardless of whether or not such claim, cost, damage, loss, or expense is caused in part by a party indemnified hereunder, except that no party shall indemnify any other party or person for their own sole negligence.
Such obligation shall not be construed to negate, abridge, or reduce other rights or obligations of indemnity which would otherwise exist as to a party or person described in this Paragraph.

C. Comprehensive General Liability
The successful Bidder shall exercise due care at all times to protect persons and property. He shall carry approved insurance from insurance companies authorized to do business in Georgia and having an A.M. Best rating of A+ or better, with the following minimums:

*The limits of insurance are as follows:
a) General liability insurance of at least One Million (1,000,000) Dollars (Combined Single Limit per occurrence) and Two Million (2,000,000) Dollars aggregate.

b) Automobile insurance of at least Five Hundred Thousand (500,000) Dollars (Combined Single Limit per accident for bodily injury or property damage); and

c) Workers’ Compensation Insurance will protect the potential bidder or offeror from the Workers’ Compensation Acts

4. Exemption from Taxes
The Contractor shall not charge the County directly for any sales or excise tax. The County is exempt from State Sales Tax. Tax Exemption Certificates indicate that the County’s tax-exempt status will be furnished by the County on request. The Contractor shall be responsible for any payment of any sales, use, or excise tax. This exemption does not include materials purchased and used by a contractor for a construction project.

5. Method of Payment
Contractors shall provide their federal employer identification number on a standard W-9 form within 15 days of the award to avoid payment delays. Contractor shall submit a payment request directly to the Brantley County Financial Coordinator for issuance.

Invoices shall be submitted to:
Brantley County Board of Commissioners 
Attn: Denise Hutchinson finance2@brantleycountyga.gov 

Upon inspection and acceptance of the work, the County will render payment, less any applicable retainment, within thirty (30) days.

6. Termination
Subject to the provisions below, the Contract may be terminated by the County upon thirty (30) days' advance written notice to the other party; but if any work or service hereunder is in progress but not completed as of the date of termination, then the Contract may be extended upon written approval of the County until said work or services are completed and accepted.
A. Termination for Convenience
The County may terminate this Contract for convenience at any time, in which case the parties shall negotiate reasonable termination costs.
B. Termination for Cause
In the event of Termination for Cause, the thirty (30) day advance notice is waived, and the Contractor shall not be entitled to termination costs.
7. Severability
In the event that any provision of this contract shall be adjudged or decreed to be invalid, such ruling shall not invalidate the entire Agreement but shall pertain only to the provision in question, and the remaining provisions shall continue to be valid, binding, and in full force and effect.

8. Applicable Laws
This contract shall be governed in all respects by the laws of the State of Georgia.


INSTRUCTIONS TO PROPOSERS

1. Completion
The proposal must show the number of days required to complete each project under normal conditions. Failure to state a completion time obligates the proposer to complete the project in accordance with the County's schedule. An unrealistically short or long promised completion may cause the proposal to be disregarded. Consistent failure to meet delivery commitments without a valid reason may result in removal from the contractor list.

2. Firm Pricing for County Acceptance
The proposal price must remain firm for County acceptance for 90 days from the proposal opening date.

3. Schedule of Required Documents
The following documents must accompany the contractor’s proposals:
Bid Form 
References
Contractor Affidavit and Agreement 
Subcontractor Affidavit and Agreement 
List of Subcontractors
Statement of Bidder’s Qualifications Contractor’s License
Contractor’s General Liability, vehicle, and workers’ compensation insurance (Certificate of Insurance)
W9


4. Authority to Bind Firm in Contract
Proposals MUST give the full firm name and address of the proposer. Failure to manually sign the proposal may result in disqualification. The person signing the proposal should show TITLE or AUTHORITY TO BIND HIS FIRM IN A CONTRACT. The firm name and an authorized signature must appear on the proposal in the space provided.

5. References
All proposers shall include, with their proposals, a list of at least three (3) current references for whom comparable work has been performed, not including the Brantley County Board of Commissioners. This list shall include the company name, the person to contact, the telephone number, the email address, the address where work is completed, and the days required to complete the work. Failure to include references may be ample cause for rejection of the proposal as non-responsive.

6. Basis for Award
The contract will be awarded to the responsible, responsive proponent whose submission, conforming to the solicitation, will be most advantageous to Brantley County – price and other factors considered. Unless otherwise specified in this RFP, Brantley County reserves the right to accept a proposal in whole or in part and to award by item or by group, whichever is deemed in the best interest of Brantley County, when applicable. Any proposer who is in default to Brantley County at the time of submitting the proposal shall have that proposal rejected. Brantley County reserves the right to clarify any contractual terms with the concurrence of the Contractor; however, any substantial nonconformity in the offer, as determined by Brantley County, shall be deemed non-responsive and the offer shall be rejected. In evaluating proposals, Brantley County shall consider the proposers' qualifications, timeframe, cost, references, and guarantees of materials and equipment.
7. Negotiation with the Responsible Prosper
Unless all proposals are canceled or rejected, the County reserves the right to negotiate with the lowest responsive, responsible proponent to obtain a contract price within the available funds whenever such proposal exceeds those funds. Negotiations with the low proposer may include modifications to both the proposed price and the specifications/scope of work to be performed.
	
8. Notice of Award
A notice of award will be issued once the Brantley County Board of Commissioners awards the project at an open meeting.

10. Scoring:

	Evaluation Criteria
	Maximum Points Value

	Total Cost
	20 Points

	Key Personnel Qualifications
	25 Points

	Team Experience
	25 Points

	References
	20 Points

	Project Approach/Timeline
	10 Points

	Total Points
	100 Points













                                   




CONTACT INFORMATION


Person to contact regarding this proposal:


Title:	

Phone: 		Fax:	

Email Address:	

Name of person authorized to bind the Firm:

Signature:	

Date:	

Name of Company:	

Address:	





















FAILURE TO RETURN THIS PAGE AS PART OF YOUR BID MAY RESULT IN THE BID BEING DEEMED NON-RESPONSIVE.

REFERENCES
The Brantley County Board of Commissioners requests a minimum of three (3) references for work of a similar size and scope.

References
Proposers shall provide references on this form.
1. Firm Name	

Brief Description of Project	

Completion Date	

Contact	Phone	

Title	E-mail	


2. Firm
Name	
Brief Description of Project	

Completion Date	

Contact	Phone	
_
Title	E-mail	



3. Firm
Name	

Brief Description of Project	

Completion Date	
Contact	Phone	

Title	E-mail	

CONTRACTOR AFFIDAVIT AND AGREEMENT

(THIS FORM SHOULD BE FULLY COMPLETED AND RETURNED WITH YOUR BID PACKET)
By executing this affidavit, the undersigned contractor verifies its compliance with O.C.G.A. § 13-10-91, stating affirmatively that the individual, firm or corporation which is engaged in the physical performance of services on behalf of the Brantley County Board of Commissioners has registered with, is authorized to use and uses the federal work authorization program commonly known as E-Verify, or any subsequent replacement program, in accordance with the applicable provisions and deadlines established in O.C.G.A. § 13-10-91.
Furthermore, the undersigned contractor will continue to use the federal work authorization program throughout the contract period and will contract for the physical performance of services in satisfaction of such contract only with subcontractors who present to the contractor an affidavit containing the information required by O.C.G.A. § 13-10-91(b). Contractor hereby attests that its federal work authorization user identification number and date of authorization are as follows:

Federal Work Authorization User Identification Number (E-Verify Number)

Date of Authorization

Name of Contractor

Address of Contractor

City, State, and Zip Code

Name of Project
I hereby declare under the penalty of perjury that the foregoing is true and correct. Executed on 	,	20	 in 	(City), 	(State).

Signature of Authorized Officer or Agent (Contractor)


Title of Authorized Officer or Agent (Contractor)


Printed Name of Authorized Officer or Agent



SUBSCRIBED AND SWORN BEFORE ME ON THIS THE
	 DAY OF            , 2026



Notary Public

My Commission



Expires:	

SUBCONTRACTOR AFFIDAVIT AND AGREEMENT
By executing this affidavit, the undersigned subcontractor verifies its compliance with O.C.G.A. 13-10-91, stating affirmatively that the individual, firm, or corporation
which is engaged in the physical performance of services under a contract with (name of contractor) on behalf of Brantley County Board of Commissioners, has registered with and is participating in a federal work authorization program* [any of the electronic verification
of work authorization programs operated by the United States Department of Homeland Security or any equivalent federal work authorization program operated by the United States Department of Homeland Security to verify information of newly hired employees, pursuant to the Immigration Reform and Control Act of 1986 (IRCA), P.L. 99-603], in accordance with the applicability provisions and deadlines established in O.C.G.A. 13- 10-91.


EEV / Basic Pilot Program* User Identification Number

BY: Authorized Officer or Agent Signature	Date (Subcontractor Name)


Title of Authorized Officer or Agent of Subcontractor


Printed Name of Authorized Officer or Agent



SUBSCRIBED AND SWORN BEFORE ME ON THIS THE
	 DAY OF, 202_



Notary Public My Commission Expires:	








FAILURE TO RETURN THIS PAGE AS PART OF YOUR BID MAY RESULT IN THE BID BEING DEEMED NON-RESPONSIVE.

BRANTLEY COUNTY BOARD OF COMMISSIONERS BRANTLEY COUNTY, GEORGIA

LIST OF SUBCONTRACTORS FORM
I do ____ propose to subcontract some of the work on this project. 
I do not propose ____ to subcontract work to the following subcontractors.


	NAME AND ADDRESS
	TYPE OF WORK

	
	

	
	

	
	

	
	

	
	

	
	

	
	

	
	

	
	

	
	

	
	

	
	



STATEMENT OF BIDDER’S QUALIFICATIONS
(To be subscribed and sworn to before a notary public)

The bidder submits the following statement of the bidder’s qualification for consideration by the Owner.

Legal Name of Bidder/Firm:	 	                                                                                                                                                                  Street Address:	 	


Telephone Number:	 	                                                                                                                                                                                  Fax Number:	 	                                                                                                                                                               Email Address:	 	                                                                                                                                                           When Organized:	 	                                                                                                                                                           Where Incorporated:	 	
Number of years engaged in the contracting business
under the present firm name:	 	                                                                                                                                 Plan of Organization:	Proprietorship Corporation Partnership

The bidder has never refused to sign a contract at the original bid. The bidder has never been declared in default on a contract.
The bidder has no Federal or Local Tax Liens.                                                             

 	T 	F

 	T 	F

    	T 	F


Remarks: 	



The foregoing statement of qualifications is submitted under oath.

Under oath, I certify that I am a principal or other representative of the firm of

 	  and I am authorized by it to execute the foregoing offer on its behalf. I am the principal person of the foregoing, with management responsibility for the subject matter, and, as such, I am personally knowledgeable of all its pertinent matters. The foregoing statements of facts in the foregoing bid are true.

I certify that this bid is made without prior understanding, agreement, or connection with any corporation, firm, or person submitting a bid for the same materials, labor, or equipment, and that it is in all respects fair and free from collusion or fraud. We understand collusive bidding is a violation of state and federal law and can result in fines, prison sentences, and civil damage awards. We agree to abide by all conditions of this bid.

The full name and addresses of persons and firms interested in the foregoing bid as principals are as follows:











Date:	 
Legal Name of Firm: 	 
By (Signature):   	
 Printed Name:  	                                                                                                                                                                         Title:  	 


Sworn to and subscribed before this day of 	202__.





						Notary Public 
My commission expires:  	











NON-COLLUSION AFFIDAVIT

COUNTY OF: _____________________________ 
STATE OF:      ________________________________ 

Before me, the Undersigned Proposer being duly sworn on oath, a Notary Public, for and in the County and State aforesaid, personally appeared ___________________________________and made oath that the Contractor herein, his agents, servants, and/or employees, to the best of his knowledge and belief, have not in any way colluded with anyone for and on behalf of the Contractor, or themselves, to obtain information that would give the Contractor an unfair advantage over others, nor have they colluded with anyone for and on behalf of the Contractor, or themselves, to gain any favoritism in the award of the contract herein. He or she further states that no person, firm, or corporation has, or will receive directly or indirectly, any rebate, fee, gift, commission, or thing of value on account of such sale.

Oath and Affirmation

I hereby affirm under the penalties for perjury that the facts and information contained in the foregoing proposal for public works are true and correct. 
Dated this day______ of ____________________, _______________

Authorized Signature for Design- Builder: _________________________________________ 

Title: ______________________________________________________________________ 

Contractor’s name (print): __________________________________________________ 

SWORN TO BEFORE ME THIS ______DAY OF_____________, 20_____ 

NOTARY PUBLIC FOR THE STATE OF ______________________ 

My Commission Expires: ______________________ 

Notary Public Signature________________________ 

Printed Name: __________________________________

Phone Number: _________________________________Address: _____________________________ 

BRANTLEY COUNTY BOARD OF COMMISSIONERS HAZARD MITIGATION PLAN
RFP#
 PROPOSAL FORM
DATE:	


TO:	BRANTLEY COUNTY BOARD OF COMMISSIONERS 33 ALLEN RD
NAHUNTA, GA 31553

Having carefully examined the Proposal Documents entitled Hazard Mitigation Plan and Addendum(s) No. (s) 	 as well as the premises and conditions affecting the work, we propose to furnish all services and labor called for them for the entire work, in accordance with the aforesaid documents, for the sum of

	Dollars
($	) which sum is hereinafter referred to as the “Base Proposal.”

If there are additional options, please provide a breakdown of the services and pricing.

We agree that this proposal may not be revoked or withdrawn for a period of ninety (90) days following such time. In the case we are notified in writing by mail or email of acceptance of this proposal within ninety (90) days after the time set for the opening of proposals.

Please provide an implementation schedule with your proposal.

Legal Name of
Firm:	
 By (Signature):
Printed Name:

Title:
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